## Summary (hidden)
SOPK EXPENDITURE DETAILS AGAINST CONTRACT OGDCL SCM SERVICES -CB-DF-206292973-4600000272-2023 FROM 1-Sep- 2023 TO 31-Aug -2025
Sr. No. | Description | Total Amount (USD) without GST | Total Amount (USD) with GST
1 | Total booked expenditure till date 31-Aug-2025) | 2048654.7577 | 2358747.2881
2 | Actual Contract Value(Sep 2023-Aug-2025) | 1342579 | 1543965.85
3 | Extended Budget cost | 717408.06 | 825019.269
4 | Total Budget cost (current) | 2059987.06 | 2368985.119
5 | Remaining cost | 11332.3023 | 13032.1477

## EXP DETAILS Sep-23 to Aug -25 (hidden)
SOPK EXPENDITURE DETAILS AGAINST CONTRACT OGDCL SCM SERVICES -CB-DF-206292973-4600000272-2023 FROM 1-Sep- 2023 TO 31st Aug -2025
Sr. No. | Invoice Date | Invoice No. | Location | Service Description | Tenure | Currency Code | Amount W/O GST | Amount Including GST | Payment Status
1 | 2023-11-01 | 068-2023 | Togh-2 | OBM Cuttings Transportation | 2023-09-01 | USD | 3875.5611 | 4456.8953 | Payment Received
2 | 2023-11-01 | 069-2023 | Chanda-7 to Togh-2 | OBM Transportation | 2023-09-01 | USD | 2201.15 | 2531.3225 | Payment Received
3 | 2023-11-28 | 073-2023 | Togh-2 | OBM Cuttings Transportation | 2023-10-01 | USD | 5743.39 | 6604.9 | Payment Received
4 | 2023-12-15 | 078-2023 | Togh-2 | OBM Cuttings Transportation | 2023-11-01 | USD | 1169.9 | 1345.38 | Payment Received
5 | 2023-12-15 | 079-2023 | Chanda-7 | OBM Cuttings Transportation | 2023-10-01 | USD | 440.38 | 506.44 | Payment Received
6 | 2023-12-15 | 080-2023 | Chanda-7 | Mud Storage Tanks | Sep-Nov 2023 | USD | 636 | 731.4 | Payment Received
7 | 2023-12-15 | 081-2023 | Togh-2 to Togh plant | OBM Transportation | 2023-11-01 | USD | 709.4 | 815.81 | Payment Received
8 | 2023-12-15 | 082-2023 | Togh-2 | Cuttings Dryer Fluid Recovery (CDFR) System | Sep-Nov 2023 | USD | 9490 | 10913.5 | Payment Received
9 | 2024-03-08 | 017-2024 | Chanda-7 (Waste pit) | Bioremediation of OBM Cuttings- Batch-7 |  | USD | 70520 | 81098 | Payment Received
10 | 2024-05-14 | 022-2024 | Chanda-7 | Bioremediation of OBM Cuttings- Batch-8 |  | USD | 27222 | 31305.3 | Payment Received
11 | 2024-05-14 | 023-2024 | Togh-2 | Bioremediation of OBM Cuttings- Batch-8 |  | USD | 46876 | 53907.4 | Payment Received
12 | 2024-05-14 | 024-2024 | Nashpa-11(Waste Pit) | Bioremediation of OBM Cuttings- Batch-8 |  | USD | 89497.5 | 102922.125 | Payment Received
13 | 2024-05-14 | 025-2024 | Chanda-7 | Mud Storage Tanks | Dec 2023 & Jan 2024 | USD | 297 | 341.55 | Payment Received
14 | 2024-05-14 | 026-2024 | Chanda-7 to Togh Plant | OBM Transportation | Nov-Dec 2023 | USD | 465.39 | 535.1985 | Payment Received
15 | 2024-05-14 | 027-2024 | Togh-2 to Togh plant | OBM Transportation | 2024-01-01 | USD | 75.47 | 86.7905 | Payment Received
16 | 2024-05-14 | 028-2024 | Togh Plant to Bettani-2 | OBM Transportation | Feb & March 2024 | USD | 14600.19 | 16790.2185 | Payment Received
17 | 2024-04-04 | 034-2024 | Togh plant to Bettani Deep-1 | OBM Transportation | Feb-Apr 2024 | USD | 297 | 341.55 | Payment Received
18 | 2024-06-07 | 051-2024 | Bettani-2 | Cuttings Dryer Fluid Recovery (CDFR) System | March-April 2024 | USD | 8636 | 9931.4 | Payment Received
19 | 2024-06-24 | 052-2024 | Bettani Deep-1 | Cuttings Dryer Fluid Recovery (CDFR) System | April-May 2024 | USD | 7064 | 8123.6 | Payment Received
20 | 2024-06-24 | 053-2024 | Bettani-2 | Cuttings Dryer Fluid Recovery (CDFR) System | 2024-05-01 | USD | 2748 | 3160.2 | Payment Received
21 | 2024-06-24 | 054-2024 | Bettani-2 to Bettani Deep-1 | OBM Transportation | 2024-05-01 | USD | 685.0293 | 787.7837 | Payment Received
22 | 2024-06-24 | 055-2024 | Nashpa-11 | OBM Cuttings Transportation | 2024-03-01 | USD | 26450.69 | 30418.2935 | Payment Received
23 | 2024-06-26 | 058-2024 | Bettani-2 | OBM Cuttings Transportation | March-May 2024 | USD | 33020.0491 | 37973.0565 | Payment Received
24 | 2024-06-26 | 059-2024 | Bettani Deep-1 | OBM Cuttings Transportation | Apr-May 2024 | USD | 25227.4187 | 29011.5315 | Payment Received
25 | 2024-06-26 | 060-2024 | bettani Deep-1(Wali-1) | OBM Cuttings Transportation | Apr-May 2024 | USD | 12080.1615 | 13892.1857 | Payment Received
26 | 2024-10-01 | 061-2024 | Togh plant | Mud Storage Tanks | Sep 2023-Apr 2024 | USD | 2436 | 2801.4 | Payment Received
27 | 2024-10-01 | 062-2024 | Sughri North-1 | Cuttings Dryer Fluid Recovery (CDFR) System | 2024-06-01 | USD | 4772 | 5535.52 | Payment Received
28 | 2024-10-01 | 063-2024 | Bettani Deep-1 | Cuttings Dryer Fluid Recovery (CDFR) System & OBM Storage Tanks | 2024-06-01 | USD | 4728 | 5437.2 | Payment Received
29 | 2024-10-01 | 066-2024 | Sughri North-1 | Cuttings Dryer Fluid Recovery (CDFR) System | JUL & AUG 2024 | USD | 9440 | 10950.4 | Payment Received
30 | 2024-10-01 | 075-2024 | Bettani-2 | Cuttings Dryer Fluid Recovery (CDFR) System | JUL & AUG 2024 | USD | 6488 | 7461.2 | Payment Received
31 | 2024-11-01 | 077-2025 | Sughri North-1 | Cuttings Dryer Fluid Recovery (CDFR) System | 2024-09-01 | Sep | 4728 | 5484.48 | Payment Received
32 | 2024-11-01 | 078-2024 | Bettani Deep-1 | Cuttings Dryer Fluid Recovery (CDFR) System & OBM Storage Tanks | Jul-Sept 2024 | USD | 8364 | 9618.6 | Payment Received
33 | 2024-11-01 | 079-2024 | Sughri North-1 | Bioremediation of OBM Cuttings- Batch-1 |  | USD | 53000 | 61480 | Payment Received
34 | 2024-11-01 | 106-2024 | Tolgh-2 | Bioremediation of OBM Cuttings- Batch-9 |  | USD | 5701.25 | 6556.4375 | Payment Received
35 | 2024-11-01 | 107-2024 | Nashpa-11 | Bioremediation of OBM Cuttings- Batch-9 |  | USD | 262668.25 | 302068.4875 | Payment Received
36 | 2024-11-01 | 108-2024 | Bettani-2 | Bioremediation of OBM Cuttings- Batch-9 |  | USD | 55524.75 | 63853.4625 | Payment Received
37 | 2024-11-01 | 109-2024 | Wali-1 | Bioremediation of OBM Cuttings- Batch-9 |  | USD | 18318.75 | 21066.5625 | Payment Received
38 | 2024-11-01 | 110-2024 | Bettani Deep-1 | Bioremediation of OBM Cuttings- Batch-9 |  | USD | 18030.5 | 20735.075 | Payment Received
39 | 2024-12-02 | 117-2024 | Sughri North-1 | Cuttings Dryer Fluid Recovery (CDFR) System | oct-Nov 2024 | USD | 9052 | 10500.32 | Payment Received
40 | 2024-12-02 | 118-2024 | Bettani-2 | Cuttings Dryer Fluid Recovery (CDFR) System | Sep-Nov 2024 | USD | 10334 | 11884.1 | Payment Received
41 | 2024-12-20 | 119-2024 | Chanda-7(WBM Pit) | OBM Cuttings Transportation | 2024-11-01 | USD | 20088.99 | 23102.3385 | Payment Received
42 | 2024-12-20 | 120-2024 | Bettani-2 to Bettani Deep-1 | OBM Transportation | Aug-Oct 2024 | USD | 105.66 | 121.509 | Payment Received
43 | 2024-12-20 | 121-2024 | Bettani-2 to Sughri North-1 | OBM Transportation | May-Jun 2024 | USD | 5755.96 | 6676.9136 | Payment Received
44 | 2024-12-20 | 122-2024 | Togh plant to Bettani Deep-1 | OBM Transportation | Sept- Oct 2024 | USD | 5199.75 | 5979.7125 | Payment Received
45 | 2024-12-20 | 123-2024 | Bettani Deep-1 to Sughri North-1 | OBM Transportation | May-Jun 2024 | USD | 5954.2 | 6906.872 | Payment Received
46 | 2024-12-20 | 124-2024 | Sughri North-1 to Togh plant | OBM Transportation | 2024-08-01 | USD | 1816.51 | 2107.1516 | Payment Received
47 | 2024-12-20 | 125-2024 | Sughri North-1 to Togh plant | OBM Transportation | 2024-11-01 | USD | 4509.97 | 5231.5652 | Payment Received
48 | 2024-12-20 | 126-2024 | Bettani Deep-1 to Bettani-2 | OBM Transportation | 2024-07-01 | USD | 221.69 | 254.9435 | Payment Received
49 | 2024-12-20 | 127-2024 | Bettani Deep-1 to Bettani-2 | OBM Transportation | 2024-08-01 | USD | 148.11 | 170.3265 | Payment Received
50 | 2024-12-20 | 128-2024 | Bettani Deep-1 | OBM Cuttings Transportation | Jun-Jul 2024 | USD | 31396.79 | 36106.3085 | Payment Received
51 | 2024-12-20 | 129-2024 | Bettani-2 | OBM Cuttings Transportation | Jun-Nov 2024 | USD | 11594.39 | 13333.5485 | Payment Received
52 | 2024-12-20 | 132-2024 | Bitani Deep-1 to Sughri North-1 | OBM Transportation | 2024-06-01 | USD | 2480.92 | 2877.8672 | Payment Received
53 | 2024-12-20 | 133-2024 | Bettani-2 to Bettani Deep-1 | OBM Transportation | Nov-Dec 2023 | USD | 282.06 | 324.369 | Payment Received
54 | 2025-02-25 | 015-2025 | Bettani Deep-1 | Cuttings Dryer Fluid Recovery (CDFR) System & OBM Storage Tanks | Dec 2024 & Jan 2025 | USD | 10428 | 11992.2 | Payment Received
55 | 2025-02-25 | 016-2025 | Sughri North-1 | Cuttings Dryer Fluid Recovery (CDFR) System | Dec 2024 & Jan 2025 | USD | 8144 | 9447.04 | Payment Received
56 | 2025-02-25 | 017-2025 | Bettani-2 | Bioremediation of OBM Cuttings- Batch-10 |  | USD | 43359.5 | 49863.425 | Payment Received
57 | 2025-02-25 | 018-2025 | WALI-1 | Bioremediation of OBM Cuttings- Batch-10 |  | USD | 12703.75 | 14609.3125 | Payment Received
58 | 2025-02-25 | 019-2025 | Bettani Deep-1 | Bioremediation of OBM Cuttings- Batch-10 |  | USD | 148906.5 | 171242.475 | Payment Received
59 | 2025-02-25 | 020-2025 | Sughri North-1 | Bioremediation of OBM Cuttings- Batch-2 |  | USD | 113950 | 132182 | Payment Received
60 | 2025-02-25 | 021-2025 | Chanda-7 (Waste pit) | OBM Cuttings Transportation | 2024-12-01 | USD | 27024.679 | 31078.3808 | Payment Received
61 | 2025-02-25 | 022-2025 | Togh Plant | OBM Cuttings Transportation | 2024-12-01 | USD | 1299.43 | 1494.3445 | Payment Received
62 | 2025-05-02 | 023-2025 | Bettani-2 | OBM Cuttings Transportation | Nov 2024 to Jan 2025 | USD | 7937.27 | 9127.8605 | Payment Received
63 | 2025-05-02 | 025-2025 | Nashpa X-5(Waste Pit) | OBM Cuttings Transportation | 2025-04-01 | USD | 9789.92 | 11258.408 | Payment Received
64 | 2025-05-02 | 052-2025 | Baragzai-1 | Cuttings Dryer Fluid Recovery (CDFR) System | Jan-Mar 2025 | USD | 10742 | 12353.3 | Payment Received
65 | 2025-05-02 | 053-2025 | Bettani Deep-1 | Cuttings Dryer Fluid Recovery (CDFR) System & OBM Storage Tanks | Feb-Apr 2025 | USD | 9764 | 11228.6 | Payment Received
66 | 2025-06-26 | 054-2025 | Bettani Deep-1 to Togh plant | OBM Transportation | FEB-MAR 2025 | USD | 7459.6376 | 8578.5833 | Payment Received
67 | 2025-06-26 | 055-2025 | Sughri North-1 to Togh plant | OBM Transportation | Jan- Mar 2025 | USD | 1503.32 | 1743.8512 | Payment Received
68 | 2025-06-26 | 056-2025 | Baragzai-1 | Cuttings Dryer Fluid Recovery (CDFR) System | April-May 2025 | USD | 8116 | 9333.4 | Payment Received
69 | 2025-06-26 | 057-2025 | Baragzai-1 | Mud Storage Tanks | Feb-May 2025 | USD | 300 | 345 | Payment Received
70 | 2025-06-26 | 058-2025 | Sughri North-1 | Mud Storage Tanks | Jan-Feb 2025 | USD | 180 | 207 | Payment Received
71 | 2025-07-03 | 070-2025 | Bettani Deep-1 | Bioremediation of OBM Cuttings- Batch-11 |  | USD | 18418.5 | 21181.275 | Payment Received
72 | 2025-07-03 | 073-2025 | Togh plant | OBM Cuttings Transportation | 2025-05-01 | USD | 6860.1355 | 7889.1559 | Payment Received
73 | 2025-07-03 | 074-2025 | Sughri North-1 to Baragzai-1 | OBM Transportation | Jan-Mar 2025 | USD | 14789.28 | 17007.672 | Payment Received
74 | 2025-07-03 | 075-2025 | Baragzai-1 | Cuttings Dryer Fluid Recovery (CDFR) System | 2025-06-01 | USD | 3936 | 4526.4 | Payment Received
75 | 2025-07-03 | 078-2025 | Togh Plant to Baragzai-1 | OBM Transportation | April-May 2025 | USD | 7646.292 | 8793.2358 | Payment Received
76 | 2025-07-03 | 079-2025 | Bettani Deep-1 to Bragzai-1 | OBM Transportation | April 2025 | USD | 4393.56 | 5052.594 | Payment Received
77 | 2025-08-01 | 087-2025 | Bettani Deep-1 | Mud Storage Tanks | May & June 2025 | USD | 732 | 841.8 | Payment Received
78 | 2025-07-03 | 072-2025 | Chanda-7 | Bioremediation of OBM Cuttings- Batch-11 |  | USD | 197472.5 | 227093.375 | Payment Received
79 | 2025-07-03 | 079-2025 | Togh plant | Bioremediation of OBM Cuttings- Batch-11 |  | USD | 5668.75 | 6519.0625 | Payment Received
80 | 2025-10-08 | 071-2025 | Baragzai-1 | Bioremediation of OBM Cuttings- Batch-11 |  | USD | 66996.65 | 77046.1475 | Payment Received
81 | 2025-07-03 | 077-2025 | Bettani Deep-1 to Bragzai-1 | OBM Transportation | April-May 2025 | USD | 4351.48 | 5004.202 | Payment Received
82 | 2025-08-11 | 091-2025 | Baragzai-1 | Cuttings Dryer Fluid Recovery (CDFR) System | 2025-07-01 | USD | 4633 | 5327.95 | Payment Received
83 | 2025-08-11 | 092-2025 | Gurgalot-1 | Cuttings Dryer Fluid Recovery (CDFR) System | 2025-07-01 | USD | 1204 | 1384.6 | Payment Received
84 | 2025-08-19 | 093-2025 | Bettani Deep-1 to Gurgalot-1 | OBM Transportation | 2025-07-01 | USD | 1979 | 2275.85 | Payment Received
85 | 2025-08-19 | 094-2025 | Baragzai-1 to Gurgaot-1 | OBM Transportation | 2025-07-01 | USD | 2065.94 | 2375.831 | Payment Received
86 | 2025-08-20 | 096-2025 | bettani Deep-1 | Mud Storage Tanks | 2025-07-01 | USD | 372 | 427.8 | Payment Received
87 | 2025-09-15 | 102-2025 | bettani Deep-1 | Mud Storage Tanks | 2025-08-01 | USD | 318 | 365.7 | Payment Received
88 | 2025-09-17 | 103-2025 | Gurgalot-1 | Cuttings Dryer Fluid Recovery (CDFR) System | July & Aug 2025 | USD | 5960 | 6854 | Payment Received
89 | 2025-09-15 | 104-2025 | Baragzai-1 | Cuttings Dryer Fluid Recovery (CDFR) System | 2025-08-01 | USD | 4345 | 4996.75 | Payment Received
90 | 2025-10-01 | 121-2025 | Baragzai-1 | OBM Cuttings Transportation | Jan-Feb 2025 | USD | 11461.446 | 13180.6629 | Payment Received
91 | 2025-10-31 | 124-2025 | Bettani Deep-1 to Gurgalot-1 | OBM Transportation | 2025-08-01 | USD | 4084.78 | 4697.5 | Payment Received
92 | 2025-10-28 | 024-2025 | Bettani Deep-1 | OBM Cuttings Transportation | (Aug-Sept 2024 | USD | 15835.39 | 18210.6985 | Invoice sent. Payment not received yet.
93 | 2025-07-03 | 067-2025 | Sughri North-1 | Bioremediation of OBM Cuttings -Batch-3 |  | USD | 54325 | 63017 | Invoice sent. Payment not received yet.
94 | 2025-07-03 | 080-2025 | Bettani-2 | Bioremediation of OBM Cuttings- Batch-11 |  | USD | 38522.5 | 44300.875 | Invoice sent. Payment not received yet.
95 | 2025-10-01 | 076-2025 | Bettani Deep-1 | OBM Cuttings Transportation | Dec-2024- July 2025 | USD | 13153.27 | 15126.2605 | Invoice sent. Payment not received yet.
96 | 2025-10-28 | 081-2025 | Gurgalot-1 | OBM Cuttings Transportation | Jul-Aug 2025 | USD | 13189.05 | 15167.4075 | Invoice sent. Payment not received yet.
97 | 2025-10-31 | 125-2025 | Baragzai-1 to Gurgalot-1 | OBM Transportation | 2025-08-01 | USD | 1415.03 | 1627.28 | Invoice sent. Payment not received yet.
98 | 2025-11-03 | 122-2025 | Togh plant | Bioremediation of OBM Cuttings -Batch-12 |  | USD | 30038.25 | 34543.9875 | Invoice sent. Payment not received yet.
99 | 2025-11-03 | 123-2025 | Nashpa X-5 | Bioremediation of OBM Cuttings -Batch-12 |  | USD | 88837.75 | 102163.4125 | Invoice sent. Payment not received yet.
100 | 2025-11-03 | 127-2025 | Togh-2 | Bioremediation of OBM Cuttings -Batch-12 |  | USD | 1147.75 | 1319.9125 | Invoice sent. Payment not received yet.
101 | 2025-11-03 | 128-2025 | Bettani Deep-1 | Bioremediation of OBM Cuttings -Batch-12 |  | USD | 19138.25 | 22008.9875 | Invoice sent. Payment not received yet.
102 | 2025-11-21 | 129-2025 | Bargzai-1 | OBM Cuttings Transportation | Mar-May 2025 | USD | 8979.59 | 10326.5285 | Invoice sent. Payment not received yet.
103 | 2025-01-01 | 005-2026 | Bargzai-1 | OBM Cuttings Transportation | Jul-Aug 2025 | USD | 8282.4278 | 9524.7919 | Invoice sent. Payment not received yet.
104 | 2025-11-01 | 006-2026 | Togh plant | Cleaning & Washing of Tanks | 2025-05-01 | USD | 13326 | 15324.9 | Invoice sent. Payment not received yet.
[6 empty] | TOTAL | 2048654.7577 | 2358747.2881
SUMMARY
|  |  |  | TOTAL EXPENDITURE |  | Expenditure up till 31- Aug , 2025 | Invoices submitted to OGDCL | Invoices submitted & paid by OGDCL | Invoices not paid yet
[6 empty] | 2048654.7577 | 2048654.7577 | 1742464.5 | 306190.2577
[6 empty] | 2358747.2881 | 2358747.2881 | 2006085.25 | 352662.0381

## Exp Details Sep-25 to June-26
SOPK EXPENDITURE DETAILS AGAINST CONTRACT OGDCL-SCM SERVICES-CB-DF-DOC288082970-2025 FROM 1-Sept, 2025 TO 30th June, 2026
| Sr. No. | Invoice Date | Invoice No. | Location | Service Description | Tenure | Currency Code | Amount W/O GST | Amount Including GST | Payment Status
| 1 | 2025-10-22 | 117-2025 | Gurgalot-1 | Cuttings Dryer Fluid Recovery (CDFR) System | 2025-09-01 | USD | 8400 | 9660 | Payment received
| 2 | 2025-10-30 | 120-2025 | Baragzai-1 | Cuttings Dryer Fluid Recovery (CDFR) System | 2025-09-01 | USD | 9780 | 11247 | Payment received
| 3 | 2025-12-31 | 133-2025 | Gurgalot-1 | OBM Cuttings Transportation | 2025-11-01 | USD | 14940.22 | 17181.253 | Payment received
| 4 | 2025-11-10 | 134-2025 | Bettani Deep-1 | Mud Storage Tanks | 2025-09-01 | USD | 9100 | 10465 | Payment received
| 5 | 2025-12-31 | 135-2025 | Bettani Deep-1 to Togh plant | OBM Transportation | Sep-Oct 2025 | USD | 19065.7324 | 21925.5923 | Payment is pending
| 6 | 2025-11-12 | 136-2025 | Bettani Deep-1 to Gurgalot-1 | OBM Transportation | 2025-10-01 | USD | 4000.5587 | 4600.6425 | Payment received
| 7 | 2025-11-12 | 137-2025 | Togh Plant to Gurgalot-1 | OBM Transportation | 2025-10-01 | USD | 3085.1318 | 3547.9016 | Payment received
| 8 | 2025-11-12 | 138-2025 | Gurgalot-1 to Togh Plant | OBM Transportation | 2025-10-01 | USD | 2338.5018 | 2689.277 | Payment received
| 9 | 2025-11-12 | 139-2025 | Gurgalot-1 | Cuttings Dryer Fluid Recovery (CDFR) System | 2025-10-01 | USD | 8952 | 10294.8 | Payment received
| 10 | 2025-12-22 | 140-2025 | Baragzai-1 | Bioremediation of OBM Cuttings- Batch-12 |  | USD | 52598.2 | 60487.93 | Payment received
| 11 | 2025-11-18 | 141-2025 | Gurgalot-1 | OBM Cuttings Transportation | Sep-Oct 2025 | USD | 25185.8059 | 28963.6768 | Payment received
| 12 | 2025-11-22 | 142-2025 | Bettani Deep-1 | OBM Cuttings Transportation | 2025-10-01 | USD | 1179.776 | 1356.7424 | Payment is pending | .
| 13 | 2025-11-19 | 143-2025 | Baragzai-1 | Cuttings Dryer Fluid Recovery (CDFR) System & Tanks | 2025-10-01 | USD | 10642 | 12238.3 | Payment received
| 14 | 2025-12-08 | 150-2025 | Gurgalot-1 | Cuttings Dryer Fluid Recovery (CDFR) System & Tanks | 2025-11-01 | USD | 7780 | 8947 | Payment received
151-2025- OGDCL INVOICE OBM TRANS - Gurgalot TO togh plant November 25 | 15 | 2025-12-16 | 151-2205 | Gurgalot-1 to Togh Plant | OBM Transportation | 2025-11-01 | USD | 1972.23 | 2268.0645 | Payment received
| 16 | 2025-12-16 | 152-2025 | Baragzai-1 to Gurgalot-1 | OBM Transportation | Oct-Nov 2025 | USD | 13669.14 | 15719.511 | Payment received
| 17 | 2025-12-16 | 153-2025 | Baragzai-1 to Togh Plant | OBM Transportation | Nov-Dec 2025 | USD | 22504.56 | 25880.244 | Payment received
| 18 | 2025-12-18 | 155-2025 | Baragzai-1 | Cuttings Dryer Fluid Recovery (CDFR) System & Tanks | 2025-11-01 | USD | 8748 | 10060.2 | Payment received
| 19 | 2026-01-14 | 002-2026 | Gurgalot-1 | Cuttings Dryer Fluid Recovery (CDFR) System & Tanks | 2025-12-01 | USD | 11630 | 13374.5 | Payment is pending
| 20 | 2026-01-14 | 003-2026 | Baragzai-1 | Mud Storage Tanks | 2025-12-01 | USD | 980 | 1127 | Payment is pending
| 21 | 2026-01-14 | 004-2026 | Togh Plant to Gurgalot-1 | OBM Transportation | 2025-12-01 | USD | 1408.74 | 1620.051 | Payment is pending
| 22 | 2026-01-02 | 007-2026 | Baragzai-1 | OBM Cuttings Transportation | Sep-Oct 2025 | USD | 5265.15 | 6054.9225 | Payment is pending
| 23 | 2026-01-02 | 008-2026 | Baragzai-1 | OBM Cuttings Transportation | Nov-Dec 2025 | USD | 8234.2 | 9469.33 | Payment is pending
| 24 | 2026-01-28 | 009-2026 | Gurgalot-1 | OBM Cuttings Transportation | 2025-12-01 | USD | 16279.64 | 18721.586 | Payment is pending
| 25 | 2026-04-01 | 010-2026 | Wali-1 | OnSite Bioremediation of OBM Cuttings(Batch-1) | Sep-Dec 2025 | USD | 320000 | 368000 | Payment is pending
| 26 | 2026-02-25 | 019-2026 | Gurgalot-1 | Cuttings Dryer Fluid Recovery (CDFR) System & Tanks | 2026-01-01 | USD | 12452 | 14319.8 | Payment is pending
| 27 | 2026-02-25 | O18-2026 | Togh Plant to Gurgalot-1 | OBM Transportation | 2026-01-01 | USD | 2676.6 | 3078.09 | Payment is pending
| 28 | 2026-02-25 | 020-2026 | Gurgalot-1 to Togh Plant | OBM Transportation | 2025-12-01 | USD | 1972.23 | 2268.0645 | Payment is pending
| 29 | 2026-02-25 | O21-2026 | Gurgalot-1 | OBM Cuttings Transportation | 2026-01-01 | USD | 6611.59 | 7603.3285 | Payment is pending
| 30 | 2026-03-25 | 024-2026 | Gurgalot-1 | Cuttings Dryer Fluid Recovery (CDFR) System & Tanks | 2026-02-01 | USD | 11456 | 13174.4 | Payment is pending
| 31 | 2026-04-07 | 031-2026 | Baragzai-1 | OBM Cuttings Transportation | 2026-03-01 | USD | 683.05 | 785.5075 | Payment is pending
| 32 | 2026-04-01 | O25-2026 | Gurgalot-1 | OBM Cuttings Transportation | Feb & Mar 2026 | USD | 15911.35 | 18298.0525 | Payment is pending
| 33 | 2026-04-15 | 035-2026 | Gurgalot-1 | Cuttings Dryer Fluid Recovery (CDFR) System & Tanks | 2026-03-01 | USD | 11510 | 13236.5 | Payment is pending
| 34 | 2026-05-19 | 039-2026 | Betani Deep-1 | Bioremediation of OBM Cuttings- Batch-13 | Dec- 25 to Feb -2026 | USD | 4601.25 | 5291.4375 | Payment is pending
| 35 | 2026-05-19 | 040-2026 | Gurgalot-1 | Bioremediation of OBM Cuttings- Batch-13 | Dec- 25 to Feb -2026 | USD | 153962.75 | 177057.1625 | Payment is pending
| 36 | 2026-05-19 | 041-2026 | Bragzai-1 | Bioremediation of OBM Cuttings- Batch-13 | Dec- 25 to Feb -2026 | USD | 93412.25 | 107424.0875 | Payment is pending
| 37 | 2026-05-14 | 043-2026 | Gurgalot-1 | Cuttings Dryer Fluid Recovery (CDFR) System & Tanks | 2026-04-01 | USD | 11280 | 12972 | Payment is pending
| 38 | 2026-05-09 | 044-2026 | Baragzai-1 | OBM Cuttings Transportation | 2026-04-01 | USD | 637.8 | 733.47 | Payment is pending
| 39 | 2026-06-10 | 045-2026 | Gurgalot-1 | Cuttings Dryer Fluid Recovery (CDFR) System & Tanks | 2026-05-01 | USD | 12332 | 14181.8 | Payment is pending
| 40 | 2026-06-11 | 046-2026 | Gurgalot-1 to Togh Plant | OBM Transportation | 2026-05-01 | USD | 1690.48 | 1944.052 | Payment is pending
| 41 | 2026-06-11 | O47-2026 | Gurgalot-1 | OBM Cuttings Transportation | Apr-May -26 | USD | 4879.56 | 5611.494 | Payment is pending
| 42 |  | O48-2026 | Gurgalot-1 | OBM Cuttings Transportation | 2026-06-01 | USD | 1948.019 | 2240.2219 | To be invoiced
| 43 |  | O49-2026 | Togh Plant to Ghari X2 | OBM Transportation | 2026-06-01 | USD | 13382.992 | 15390.4408 | To be invoiced
| 44 |  | 050-2026 | Gurgalot-1 | Cuttings Dryer Fluid Recovery (CDFR) System & Tanks | 2026-06-01 | USD | 11760 | 13524 | To be invoiced
[7 empty] | TOTAL | 960899.5076 | 1105034.4338
SUMMARY
|  |  | TOTAL EXPENDITURE |  | Expenditure up till 30- June , 2026 | Invoices submitted to OGDC | Invoices submitted & paid by OGDC | Invoices yet not submitted to OGDC | Invoices yet to be paid by OGDC
|  |  | Total Amount Witout GST |  | 960899.5076 | 933808.5 | 290272.23 | 27091.01 | 643536.27
|  |  | Total Amount With GST |  | 1105034.4338 | 1073879.775 | 333813.0645 | 31154.6615 | 740066.7105

## Additional Bugdet Working (hidden)
| Services | Well-ID | Period | Cost USD (Without GST) | Cost USD (With GST)
1 | CDFR | Baragzai-1 | Jun-July 2025 | 4700 | 5452
|  | Gulgolot X-1 | June-Aug 2025 (Section 17.5' & 12.24') | 13500 | 15525
A . | TOTAL |  |  | 18200 | 20977
2 | OBM Cuttings Transportation
Estimated Volume
|  | BarakhZai-1 | Jun-Aug 2025 | 8550 | 9832.5 | 1000 tons
|  | Gulgolot X-1 | Jun-Aug 2025 | 28500 | 32775 | 3000 tons
B | TOTAL |  |  | 37050 | 42607.5
3 | OBM Transportation | BetaniDeep-1 to Baragzai-1 | Jun-Aug 2025 | 16602.96 | 19093.404 | 400m3
|  | Others (To & Fro ) OGDCL Sites | Jun-Aug 2025 | 18867 | 21885.72 | 1000 m3
C | TOTAL |  |  | 35469.96 | 40979.124
4 | Bioremediation | Batch 12( Biosite Nashpa-4) | June-Aug 2025 | 202200 | 232530 | 4044 tons
|  | Gulgolot X-1 | June-Aug 2025 | 150000 | 172500 | 3000 tons
|  | BarakhZai-1 | June-Aug 2025 | 50000 | 57500 | 1000 tons
|  | Wali-1 | June-Aug 2025 | 300000 | 345000 | 6000 tons
D | TOTAL |  |  | 702200 | 807530
| TOTAL | A + B+ C +D | 792919.96 | 912093.624
|  |  | Without GST | With GST